## Artifacts
Artifact | CYC-1 | CYC-4 | Added | Changed | Unchanged | Added IDs | Changed IDs
Requirements | 128 | 138 | 10 | 3 | 125 | REQ-129, REQ-130, REQ-131, REQ-132, REQ-133, REQ-134, REQ-135, REQ-136, REQ-137, REQ-138 | REQ-122, REQ-124, REQ-126
Test cases | 132 | 144 | 12 | 6 | 126 | TC-F-129, TC-F-130, TC-F-131, TC-F-132, TC-F-133, TC-F-134, TC-F-135, TC-F-136, TC-F-137, TC-F-138, TC-F-139, TC-F-140 | TC-F-112, TC-F-115, TC-F-119, TC-F-120, TC-F-121, TC-F-122
Scripts | 58 | 65 | 7 | 3 | 55 | br-131-free-cancellation.spec.js, br-132-cancellation-outcome.spec.js, br-133-non-refundable-cancellation.spec.js, br-134-cancellation-deadline-email.spec.js, br-135-ops-retry-limit.spec.js, br-136-cancellation-email.spec.js, br-137-cancellation-email-failure.spec.js | br-122-cart-expiry.spec.js, br-124-resend-limit.spec.js, br-126-stay-length-limit.spec.js

## Changed requirements
ID | Before (CYC-1) | After (CYC-4)
REQ-122 | A cart expires 30 minutes after it is created and never creates a reservation itself. | A cart expires 20 minutes after it is created and never creates a reservation itself.
REQ-124 | A confirmation can be resent at most 3 times per booking in 24 hours. | A confirmation can be resent at most 5 times per booking in 24 hours.
REQ-126 | A stay can be at most 30 nights; Paris (PAR) allows at most 21 nights. | A stay can be at most 30 nights; Paris (PAR) allows at most 14 nights.

## Execution
Metric | CYC-1 | CYC-4
executed | 74 | 83
passed | 71 | 79
failed | 3 | 4
passRate | 95.9 | 95.2

## Defects
Movement | Defect IDs
CYC-1 defects | DEF-001, DEF-002, DEF-003
CYC-4 defects | DEF-001, DEF-002, DEF-007, DEF-008
new | DEF-007, DEF-008
still open | DEF-001, DEF-002
resolved | DEF-003